## Sheet1
Key | Summary | Assignee | Status | Resolution | Created | Start Date | End Date | Comment Author | Comment Time | Comment
GPMT-52 | DDL Request | Yesho Arisa | Completed |  | 2025-02-03 | 2025-02-04 | 2025-02-11 |  |  | Reviewed and closed.
GPMT-53 | Data load request (DML) | Yesho Arisa | Completed |  | 2025-02-03 | 2025-02-06 | 2025-02-18 |  |  | Reviewed and closed.
GPMT-67 | Run stats on all the tables | Yesho Arisa | Completed |  | 2025-02-18 | 2025-02-18 | 2025-02-28 |  |  | Reviewed and closed.
GPMT-68 | Load data for the newly created tables. | Yesho Arisa | Completed |  | 2025-02-18 | 2025-02-18 | 2025-03-07 |  |  | Reviewed and closed.
GPMT-84 | Add index or cleanup unwanted indexes from the app schema | Yesho Arisa | InProgress |  | 2025-03-05 | 2025-03-07