## Sheet1
Key | Summary | Assignee | Status | Resolution | Created | Start Date | End Date | Comment Author | Comment Time | Comment
GPMT-52 | DDL Request | Yesho Arisa | Completed |  | 2025-02-03 | 2025-02-04 | 2025-02-11 |  |  | Reviewed and closed.
GPMT-53 | Data load request (DML) | Yesho Arisa | Completed |  | 2025-02-03 | 2025-02-06 | 2025-02-18 |  |  | Reviewed and closed.
GPMT-67 | Run stats on all the tables | Yesho Arisa | Completed |  | 2025-02-18 | 2025-02-18 | 2025-02-28 |  |  | Reviewed and closed.
GPMT-68 | Load data for the newly created tables. | Yesho Arisa | Completed |  | 2025-02-18 | 2025-02-18 | 2025-03-07 |  |  | Reviewed and closed.
GPMT-84 | Add index or cleanup unwanted indexes from the app schema | Yesho Arisa | Completed |  | 2025-03-05 | 2025-03-07 | 2025-03-14 |  |  | Reviewed and closed.
GPMT-98 | create new objects | Yesho Arisa | Completed |  | 2025-03-14 | 2025-03-17 | 2025-03-21 |  |  | Reviewed and closed.
GPMT-105 | Load data for the newly created tables. | Yesho Arisa | Completed |  | 2025-03-21 | 2025-03-24 | 2025-03-28 |  |  | Reviewed and closed.
GPMT-125 | capacity issues purge the data | Yesho Arisa | Completed |  | 2025-03-28 | 2025-04-02 | 2025-04-04 |  |  | Reviewed and closed.
GPMT-124 | Tune the slow running query | Yesho Arisa | In progress |  | 2025-03-28 | 2025-04-01