## Sheet1
| Summary | Assignee | Status | Resolution | Created | Start Date | End Date | Comment Author | Comment Time | Comment
BDA - 113 | Start Beedata Analytics project | Sunny Kumar Jha | Done |  | 2025-03-02 | 2025-03-01 | 2025-03-14 | Sunny Kumar Jha |  | Reviewed and Closed Ticket
BDA - 114 | BEEDATA ANALYTICS - Home Page | Sunny Kumar Jha | Done |  | 2025-03-17 | 2025-03-17 | 2025-03-28 | Sunny Kumar Jha |  | Reviewed and Closed Ticket
BDA - 120 | Analyzing Home Page | Sunny Kumar Jha | In-Progress |  | 2025-03-28 | 2025-03-31 |  | Sunny Kumar Jha |  | Will be Analyzing about the Home Page
BDA - 120 | Analyzing Home Page | Sunny Kumar Jha | In-Progress |  |  | 2025-03-31 | 2025-04-11 | Sunny Kumar Jha | 2025-04-04 | I will refine the Beedata Analytics homepage to clearly highlight key expertise in Data Analytics, Data Science, and Data Mining, ensuring a simple, informative, and visually engaging layout.
BDA - 120 | Analyzing Home Page | Sunny Kumar Jha | In-Progress |  |  |  | 2025-04-11 | Sunny Kumar Jha | 2025-04-11 | The analytical home page has been examined and fulfills the necessary functionality and design criteria. A clear and user-friendly layout accurately presents all key metrics.
BDA - 141 | Developing of Data Analytics Tool | Sunny Kumar Jha | To-Do |  | 2025-04-10 | 2025-04-14 | 2025-04-25 | Sunny Kumar Jha | 2025-04-11 | The analytical tool will be developing. The first tasks involve establishing data processing logic and creating the main user interface to ensure smooth operation.
BDA - 141 | Developing of Data Analytics Tool | Sunny Kumar Jha | In-Progress |  |  |  | 2025-04-25 | Sunny Kumar Jha | 2025-04-18 | The implementation of core functionalities, including data ingestion, preprocessing, and basic visualization modules, has been completed. The present emphasis is on fine-tuning the user interface and incorporating advanced analytics capabilities.