## Sheet1
Key | Summary | Assignee | Status | Resolution | Created | Start Date | End Date | Comment Author | Comment Time | Comment
AC-131 | Dashboard enhancement | Narasimha Bachu | Done |  | 2025-04-06 | 2025-03-24 | 2025-04-11 |  |  | closed the ticket
AC-135 | Settings page | Narasimha bachu | Done |  | 04/11/.2025 | 2025-04-07 | 2025-04-18 |  |  | closed the ticket
AC- 162 | Invoice tab in Settings page | Narasimha Bachu | in prpogress |  | 2025-04-21 | 2025-04-21 | 2025-04-25 |  |  | opened new ticket
AC-174 | Enhancing inovice tab in settings page | narasimha bachu | in progress |  | 2025-04-28 | 2025-04-28 | 2025-05-02 |  |  | opened new ticket
AC- 175 | email tab in settings page | narasimha Bachu | in progress |  | 2025-05-05 | 2025-05-05 | 2025-05-09 |  |  | openmed new ticket
| invoice tab in settings page | Narasimha Bachu | done |  | 2025-04-21 | 2025-04-21 | 2025-05-09 |  |  | ticket closed