| Weekly Status Report Entellects corporation Phone: 470-926-0977 DBA: Bee Data Technology 5105 Toll view Drive ste 105 Fax: Rolling Meadows IL 60008 Email: harish@bedatatech.com Timesheets@bedatatech.com www.beedatatechnology.com |  |
| --- | --- |
| Date of Report: | 05/30/2025 |
| Date Range | 05/26/2025 - 05/30/2025 No of hours (M-4,T-4,W-4,Thu-4, F-4 total 20) |
| Consultant Information: | Name: Entellects corporation Cell: Email: Client Name: Internal product Work Location Address: Home/Office |
| Project/Work: | Go-To-Market |
| Summary of Activities in the last week: | GTM Strategy Finalized – Aligned on target audience, value proposition, positioning, and defined key launch KPIs. Marketing Assets & Channel Setup Completed – Created core marketing content, designed visuals, and configured email, social, and paid media channels for launch readiness. |
| Goals and objectives for next week: | Execute Soft Launch & Monitor Performance – Launch to a limited audience, track key metrics (e.g. sign-ups, engagement), and validate user journey. Gather Feedback & Optimize – Collect qualitative and quantitative feedback, identify friction points, and implement quick fixes or improvements for full launch. |
| Employee Signature | Harish Kumar Sure |