## Sheet1
Key | Summary | Assignee | Status | Resolution | Created | Start Date | End Date | Comment Author | Comment Time | Comment
https://beedatatechnology.atlassian.net/browse/EM-189 | Analysis - Create Payroll Summary Screen | Sowmya Gaduputi |  | done | 2025-05-22 | 2025-05-23 | 2025-05-27 |  |  | Added comments in JIRA
https://beedatatechnology.atlassian.net/browse/EM-190 | Design - Create Payroll Summary Screen | Sowmya Gaduputi |  | done | 2025-05-22 | 2025-05-27 | 2025-05-30
https://beedatatechnology.atlassian.net/browse/EM-191 | Database Design -Create Payroll Summary Screen | Sowmya Gaduputi |  | inprogress | 2025-05-22