## Sheet1
Key | Summary | Assignee | Status | Resolution | Created | Start Date | End Date | Comment Author | Comment Time | Comment
BDA-167 | Display Data Analytics Information Page | Kasindula Srikanya | In Progress |  | 2025-04-30 | 2025-04-30 |  | Kasindula Srikanya | 2025-05-05 | As a business analyst or visitor to the Beedata website, I want to view a clear and informative overview of Data Analytics, including its tools and features, so that I can understand its relevance, applications, and how Beedata’s solutions can support data-driven decision-making.
BDA-167 | Display Data Analytics Information Page | Kasindula Srikanya | Done |  | 2025-04-30 | 2025-05-28 |  | Kasindula Srikanya | 2025-05-28 | Sprint Completed
BDA-213 | SQL Automation & Database Migrations | Kasindula Srikanya | In Progress |  | 2025-06-09 | 2025-06-09 |  | Kasindula Srikanya | 2025-06-09 | Automate SQL tasks and facilitate seamless database migrations, ensuring efficient and error-free data transfer between environments (e.g., from on-prem to AWS RDS, PostgreSQL to Aurora, or between different databases).
BDA-223 | Product Information Page | Kasindula Srikanya | In Progress |  | 2025-06-16 | 2025-06-16 |  | Kasindula Srikanya | 2025-06-16 | As a user, I want to understand the features and benefits of the Data Analytics tool offered by BeeData, so that I can evaluate its value and potential use in my organization.
BDA-213 | SQL Automation & Database Migrations | Kasindula Srikanya | Done |  | 2025-06-09 | 2025-06-09 | 2025-06-23 | Kasindula Srikanya | 2025-06-23 | Sprint Completed
BDA-223 | Product Information Page | Kasindula Srikanya | Done |  | 2025-06-16 | 2025-06-18 | 2025-06-23 | Kasindula Srikanya | 2025-06-23 | Sprint Completed
BDA-226 | Create Informative Data Analytics Web Page with Visual Elements | Kasindula Srikanya | In Progress |  | 2025-06-23 | 2025-06-23 |  | Kasindula Srikanya | 2025-06-23