## Sheet1
Key | Summary | Assignee | Status | Resolution | Created | Start Date | End Date | Comment Author | Comment Time | Comment
CB - 215 | Final Touches & QA Kickoff | Harish Kumar | Completed |  | 2025-06-16 | 2025-06-16 | 2025-06-17 |  |  | Reviewed and closed.
CB - 215 | Accessibility & Responsive Testing | Harish Kumar | Completed |  | 2025-06-17 | 2025-06-17 | 2025-06-18 |  |  | Reviewed and closed.
CB - 215 | PDF UX & Error Handling | Harish Kumar | Completed |  | 2025-06-17 | 2025-06-18 | 2025-06-19 |  |  | Reviewed and closed.
CB - 215 | Analytics & Code Cleanup | Harish Kumar | Completed |  | 2025-06-18 | 2025-06-19 | 2025-06-19 |  |  | Reviewed and closed.
CB - 215 | Sprint Review & Release Prep | Harish Kumar | Completed |  | 2025-06-19 | 2025-06-19 | 2025-06-20 |  |  | Reviewed and closed.