## Sheet1
Key | Summary | Assignee | Status | Resolution | Created | Start Date | End Date | Comment Author | Comment Time | Comment
BDA-167 | Display Data Analytics Information Page | Kasindula Srikanya | In Progress |  | 2025-04-30 | 2025-04-30 |  | Kasindula Srikanya | 2025-05-05 | As a business analyst or visitor to the Beedata website, I want to view a clear and informative overview of Data Analytics, including its tools and features, so that I can understand its relevance, applications, and how Beedata’s solutions can support data-driven decision-making.
BDA-167 | Display Data Analytics Information Page | Kasindula Srikanya | Done |  | 2025-04-30 | 2025-05-28 |  | Kasindula Srikanya | 2025-05-28 | Sprint Completed
BDA-213 | SQL Automation & Database Migrations | Kasindula Srikanya | In Progress |  | 2025-06-09 | 2025-06-09 |  | Kasindula Srikanya | 2025-06-09 | Automate SQL tasks and facilitate seamless database migrations, ensuring efficient and error-free data transfer between environments (e.g., from on-prem to AWS RDS, PostgreSQL to Aurora, or between different databases).
BDA-223 | Product Information Page | Kasindula Srikanya | In Progress |  | 2025-06-16 | 2025-06-16 |  | Kasindula Srikanya | 2025-06-16 | As a user, I want to understand the features and benefits of the Data Analytics tool offered by BeeData, so that I can evaluate its value and potential use in my organization.
BDA-213 | SQL Automation & Database Migrations | Kasindula Srikanya | Done |  | 2025-06-09 | 2025-06-09 | 2025-06-23 | Kasindula Srikanya | 2025-06-23 | Sprint Completed
BDA-223 | Product Information Page | Kasindula Srikanya | Done |  | 2025-06-16 | 2025-06-18 | 2025-06-23 | Kasindula Srikanya | 2025-06-23 | Sprint Completed
BDA-226 | Create Informative Data Analytics Web Page with Visual Elements | Kasindula Srikanya | In Progress |  | 2025-06-23 | 2025-06-23 |  | Kasindula Srikanya | 2025-06-23
|  | Kasindula Srikanya | Done |  | 2025-06-23 | 2025-06-24 | 2025-07-02 | Kasindula Srikanya | 2025-07-02 | Sprint Completed
BDA-234 | Data Analytics Product Landing Page | Kasindula Srikanya | In Progress |  | 2025-07-02 | 2025-07-02 |  | Kasindula Srikanya | 2025-07-02 | As a visitor to the BeeData website, I want to land on a modern, visually appealing Data Analytics page. This page should clearly present an overview of Data Analytics, showcase key features (such as Data Analytics, Data Science, and Data Mining), and describe the Data Analytics Tool
BDA-234 | Data Analytics Product Landing Page | Kasindula Srikanya | In Progress |  | 2025-07-02 | 2025-07-02 |  | Kasindula Srikanya | 2025-07-09 | Devoloping the Data Analytics page.