## Sheet1
| Summary | Assignee | Status | Resolution | Created | Start Date | End Date | Comment Author | Comment Time | Comment
BDA - 113 | Start Beedata Analytics project | Sunny Kumar Jha | Done |  | 2025-03-02 | 2025-03-01 | 2025-03-14 | Sunny Kumar Jha |  | Reviewed and Closed Ticket
BDA - 114 | BEEDATA ANALYTICS - Home Page | Sunny Kumar Jha | Done |  | 2025-03-17 | 2025-03-17 | 2025-03-28 | Sunny Kumar Jha |  | Reviewed and Closed Ticket
BDA - 120 | Analyzing Home Page | Sunny Kumar Jha | In-Progress |  | 2025-03-28 | 2025-03-31 |  | Sunny Kumar Jha |  | Will be Analyzing about the Home Page
BDA - 120 | Analyzing Home Page | Sunny Kumar Jha | In-Progress |  |  | 2025-03-31 | 2025-04-11 | Sunny Kumar Jha | 2025-04-04 | I will refine the Beedata Analytics homepage to clearly highlight key expertise in Data Analytics, Data Science, and Data Mining, ensuring a simple, informative, and visually engaging layout.
BDA - 120 | Analyzing Home Page | Sunny Kumar Jha | In-Progress |  |  |  | 2025-04-11 | Sunny Kumar Jha | 2025-04-11 | The analytical home page has been examined and fulfills the necessary functionality and design criteria. A clear and user-friendly layout accurately presents all key metrics.
BDA - 141 | Developing of Data Analytics Tool | Sunny Kumar Jha | To-Do |  | 2025-04-10 | 2025-04-14 | 2025-04-25 | Sunny Kumar Jha | 2025-04-11 | The analytical tool will be developing. The first tasks involve establishing data processing logic and creating the main user interface to ensure smooth operation.
BDA - 141 | Developing of Data Analytics Tool | Sunny Kumar Jha | In-Progress |  |  |  | 2025-04-25 | Sunny Kumar Jha | 2025-04-18 | The implementation of core functionalities, including data ingestion, preprocessing, and basic visualization modules, has been completed. The present emphasis is on fine-tuning the user interface and incorporating advanced analytics capabilities.
BDA - 141 | Developing of Data Analytics Tool | Sunny Kumar Jha | Done |  |  |  | 2025-04-25 | Sunny Kumar Jha | 2025-04-25 | Reviewed and Closed Ticket
BDA - 161 | Data Science to enhance data analytics workflows | Sunny Kumar Jha | To-Do |  | 2025-04-25 | 2025-04-28 | 2025-05-09 | Sunny Kumar Jha | 2025-04-26 | I’ll be working on enhancing our data analytics workflows using data science techniques like predictive modeling and statistical analysis to improve insights and automation.
BDA - 161 | Data Science to enhance data analytics workflows | Sunny Kumar Jha | In-Progress |  | 2025-04-25 | 2025-04-28 | 2025-05-09 | Sunny Kumar Jha | 2025-05-02 | streamlining data workflows using Python, SQL, and dbt to improve pre-processing, automate reporting tasks, and enhance data quality. Early results show promise refinements ongoing based on feedback and performance.
BDA - 161 | Data Science to enhance data analytics workflows | Sunny Kumar Jha | Done |  | 2025-04-25 | 2025-04-28 | 2025-05-09 | Sunny Kumar Jha | 2025-05-09 | Reviewed and Closed Ticket
BDA - 183 | Perform Data Mining for Enhanced Business Analytics Insights | Sunny Kumar Jha | To-Do |  | 2025-05-08 | 2025-05-12 | 2025-05-23 | Sunny Kumar Jha | 2025-05-09 | Started initial data extraction and cleaning. Will proceed with EDA and modeling once preprocessing is complete.
BDA - 183 | Perform Data Mining for Enhanced Business Analytics Insights | Sunny Kumar Jha | In-Progress |  |  | 2025-05-12 | 2025-05-23 | Sunny Kumar Jha | 2025-05-16 | Data mining is underway—initial analysis reveals promising patterns. Proceeding with deeper insight extraction
BDA - 183 | Perform Data Mining for Enhanced Business Analytics Insights | Sunny Kumar Jha | Done |  |  |  | 2025-05-23 | Sunny Kumar Jha | 2025-05-23 | Reviewed and Closed Ticket
BDA - 199 | Develop Predictive Models Based on Mined Business Data | Sunny Kumar Jha | In-Progress |  | 2025-05-22 | 2025-05-26 | 2025-06-06 | Sunny Kumar Jha | 2025-05-23 | Starting work on developing predictive models based on the insights generated from previous data mining activities
BDA - 199 | Develop Predictive Models Based on Mined Business Data | Sunny Kumar Jha | In-Progress |  |  | 2025-05-26 | 2025-06-06 | Sunny Kumar Jha | 2025-05-30 | Completed feature selection and data preprocessing. Identified suitable ML algorithms for prototyping. No blockers so far — initial model training planned for next sprint.
BDA - 199 | Develop Predictive Models Based on Mined Business Data | Sunny Kumar Jha | Done |  |  | 2025-05-26 | 2025-06-06 | Sunny Kumar Jha | 2025-06-06 | Reviewed and Closed Ticket
BDA - 219 | Evaluating model performance in real-world scenarios | Sunny Kumar Jha | In-Progress |  |  | 2025-06-09 | 2025-06-20 | Sunny Kumar Jha | 2025-06-06 | Will validate that the predictive models behave reliably outside of controlled test environments. It ensures the models generalize well to fresh, unseen data and produce actionable insights aligned with actual business outcomes.
BDA - 219 | Evaluating model performance in real-world scenarios | Sunny Kumar Jha | In-Progress |  |  | 2025-06-09 | 2025-06-20 | Sunny Kumar Jha | 2025-06-13 | currently testing the model in real-world scenarios to assess its accuracy, robustness, and performance
BDA - 219 | Evaluating model performance in real-world scenarios | Sunny Kumar Jha | Done |  |  | 2025-06-09 | 2025-06-20 | Sunny Kumar Jha | 2025-06-20 | Reviewed and Closed Ticket
BDA - 230 | Validate Model Performance Under Production Constraints | Sunny Kumar Jha | In-Progress |  |  | 2025-06-23 | 2025-07-04 | Sunny Kumar Jha | 2025-06-20 | Validating the model under real-world system constraints to ensure it meets production SLAs for latency, memory, and scalability
BDA - 230 | Validate Model Performance Under Production Constraints | Sunny Kumar Jha | In-Progress |  |  | 2025-06-23 | 2025-07-04 | Sunny Kumar Jha | 2025-06-27 | Model performance has been validated under production constraints. Inference latency is averaging around 120ms, staying well within the target threshold, and memory usage remains below the 500MB limit at approximately 480MB. Model accuracy is stable with no significant degradation observed. A minor input data drift of around 2.5% was detected but is currently within acceptable bounds. Next steps include running an A/B test with the quantized model and setting up automated drift monitoring.
BDA - 230 | Validate Model Performance Under Production Constraints | Sunny Kumar Jha | Done |  |  | 2025-06-23 | 2025-07-04 | Sunny Kumar Jha | 2025-07-04 | Reviewed and Closed Ticket
BDA - 240 | Monitor and Optimize Model Performance Post-Deployment | Sunny Kumar Jha | To-Do |  | 2025-07-04 | 2025-07-07 | 2025-07-18 | Sunny Kumar Jha | 2025-07-04 | Setting up monitoring for the deployed model to track performance metrics, detect issues in real time, and ensure it continues to meet production requirements
BDA - 240 | Monitor and Optimize Model Performance Post-Deployment | Sunny Kumar Jha | In-Progress |  | 2025-07-04 | 2025-07-07 | 2025-07-18 | Sunny Kumar Jha | 2025-07-11 | Focus on defining retraining triggers and integrating periodic model evaluation pipelines.
BDA - 240 | Monitor and Optimize Model Performance Post-Deployment | Sunny Kumar Jha | Done |  | 2025-07-04 | 2025-07-07 | 2025-07-18 | Sunny Kumar Jha | 2025-07-18 | Reviewed and Closed Ticket
BDA - 258 | Implement Automated Model Drift Detection and Alerting Mechanism | Sunny Kumar Jha | To-Do |  | 2025-07-18 | 2025-07-21 | 2025-08-01 | Sunny Kumar Jha | 2025-07-18 | I will be implementing an automated system to monitor and detect data or concept drift in the deployed machine learning model.
BDA - 258 | Implement Automated Model Drift Detection and Alerting Mechanism | Sunny Kumar Jha | In-Progress |  |  | 2025-07-21 | 2025-08-01 | Sunny Kumar Jha | 2025-07-25 | The system now includes pipelines that continuously compare incoming data distributions with the original training data using statistical methods such as the Kolmogorov–Smirnov test and Population Stability Index (PSI). I have also incorporated drift detection algorithms like the Drift Detection Method (DDM) to identify changes in model predictions.