## Sheet1
Key | Summary | Assignee | Status | Resolution | Created | Start Date | End Date | Comment Author | Comment Time | Comment
ATB-274 | Implement Webhook Listener and Payload Parser | Shodak | Done | Completed | 2025-07-21 | 2025-07-21 | 2025-07-22 | Shodak | 2025-07-22 18:00 | Webhook endpoint using Flask successfully receives JSON payload from TradingView.
ATB-274 | Enhance Backend Signal Validation Logic | Shodak | Done | Completed | 2025-07-23 | 2025-07-23 | 2025-07-24 | Shodak | 2025-07-24 17:30 | Added duplicate trade check, RSI/Fibonacci validation, and payload integrity checks.
ATB-274 | Integrate Binance API for Live Trade Execution | Shodak | Done | Completed | 2025-07-25 | 2025-07-25 | 2025-07-26 | Shodak | 2025-07-26 16:00 | Live trades executed successfully via Binance API. Handled API key auth and error response.
ATB-274 | Risk Management Module - Position Sizing and SL/TP Calculation | Shodak | Done | Completed | 2025-07-27 | 2025-07-27 | 2025-07-29 | Shodak | 2025-07-29 19:00 | Implemented 1% risk rule, position sizing logic, dynamic and fixed SL, multi-stage TP.
ATB-274 | Log Trade Data and Build Initial Analytics Dashboard | Shodak | In Progress | Unresolved | 2025-07-30 | 2025-07-30 | 2025-08-01 | Shodak | 2025-07-31 15:00 | Trade data logging complete; basic dashboard with win rate and profit curve in progress.