## Sheet1
Key | Summary | Assignee | Status | Resolution | Created | Start Date | End Date | Comment Author | Comment Time | Comment
BDA-167 | Display Data Analytics Information Page | Kasindula Srikanya | In Progress |  | 2025-04-30 | 2025-04-30 |  | Kasindula Srikanya | 2025-05-05 | As a business analyst or visitor to the Beedata website, I want to view a clear and informative overview of Data Analytics, including its tools and features, so that I can understand its relevance, applications, and how Beedata’s solutions can support data-driven decision-making.
BDA-167 | Display Data Analytics Information Page | Kasindula Srikanya | Done |  | 2025-04-30 | 2025-05-28 |  | Kasindula Srikanya | 2025-05-28 | Sprint Completed
BDA-213 | SQL Automation & Database Migrations | Kasindula Srikanya | In Progress |  | 2025-06-09 | 2025-06-09 |  | Kasindula Srikanya | 2025-06-09 | Automate SQL tasks and facilitate seamless database migrations, ensuring efficient and error-free data transfer between environments (e.g., from on-prem to AWS RDS, PostgreSQL to Aurora, or between different databases).
BDA-223 | Product Information Page | Kasindula Srikanya | In Progress |  | 2025-06-16 | 2025-06-16 |  | Kasindula Srikanya | 2025-06-16 | As a user, I want to understand the features and benefits of the Data Analytics tool offered by BeeData, so that I can evaluate its value and potential use in my organization.
BDA-213 | SQL Automation & Database Migrations | Kasindula Srikanya | Done |  | 2025-06-09 | 2025-06-09 | 2025-06-23 | Kasindula Srikanya | 2025-06-23 | Sprint Completed
BDA-223 | Product Information Page | Kasindula Srikanya | Done |  | 2025-06-16 | 2025-06-18 | 2025-06-23 | Kasindula Srikanya | 2025-06-23 | Sprint Completed
BDA-226 | Create Informative Data Analytics Web Page with Visual Elements | Kasindula Srikanya | In Progress |  | 2025-06-23 | 2025-06-23 |  | Kasindula Srikanya | 2025-06-23
|  | Kasindula Srikanya | Done |  | 2025-06-23 | 2025-06-24 | 2025-07-02 | Kasindula Srikanya | 2025-07-02 | Sprint Completed
BDA-234 | Data Analytics Product Landing Page | Kasindula Srikanya | In Progress |  | 2025-07-02 | 2025-07-02 |  | Kasindula Srikanya | 2025-07-02 | As a visitor to the BeeData website, I want to land on a modern, visually appealing Data Analytics page. This page should clearly present an overview of Data Analytics, showcase key features (such as Data Analytics, Data Science, and Data Mining), and describe the Data Analytics Tool
BDA-234 | Data Analytics Product Landing Page | Kasindula Srikanya | In Progress |  | 2025-07-02 | 2025-07-02 |  | Kasindula Srikanya | 2025-07-09 | Devoloping the Data Analytics page.
BDA-234 | Data Analytics Product Landing Page | Kasindula Srikanya | Done |  | 2025-07-02 | 2025-07-02 | 2025-07-16 | Kasindula Srikanya | 2025-07-16 | Completion of the sprint
BDA-253 | Integrate Data Analytics Dashboard with Real-Time Data Feeds | Kasindula Srikanya | In Progress |  | 2025-07-16 | 2025-07-16 |  | Kasindula Srikanya | 2025-07-16 | As a data analytics engineer, I want to integrate the analytics dashboard with real-time data feeds so that business users can view up-to-date metrics and trends without manual refresh. This will improve the decision-making process and ensure the dashboard always displays the latest insights.
BDA-253 | Integrate Data Analytics Dashboard with Real-Time Data Feeds | Kasindula Srikanya | Done |  | 2025-07-16 | 2025-07-16 | 2025-07-30 | Kasindula Srikanya | 2025-07-22 | Continuattion of the sprint
BDA-271 | Data Analytics landing page | Kasindula Srikanya | In Progress |  | 2025-07-30 | 2025-07-30 |  | Kasindula Srikanya | 2025-07-30 | As afirst-time visitor or potential customer,I want to learn about BeeData’s Data Analytics capabilities through a clean, informative web interface,so that I can understand the benefits and features of the tool before deciding to explore further or download it.
BDA-271 | Data Analytics landing page | Kasindula Srikanya | Done |  | 2025-07-30 | 2025-07-30 | 2025-08-04 | Kasindula Srikanya | 2025-08-04 | Continuattion of the sprint
BDA-279 | Data Analytics Features and Tool Info | Kasindula Srikanya | In Progress |  | 2025-08-04 | 2025-08-04 |  | Kasindula Srikanya | 2025-08-04 | As a visitor, I want to understand the concept and benefits of Data Analytics and its tools so that I can evaluate its relevance to my business.