## Sheet1
Key | Summary | Assignee | Status | Resolution | Created | Start Date | End Date | Comment Author | Comment Time | Comment
SAA-262 | Final improvements to parsing & backend wiring | Harish Kumar | Completed |  | 2025-08-04 | 2025-08-04 | 2025-08-05 |  |  | Reviewed and closed.
SAA-262 | Implement job matching logic | Harish Kumar | Completed |  | 2025-08-05 | 2025-08-05 | 2025-08-06 |  |  | Reviewed and closed.
SAA-262 | Frontend integration + dashboard polish | Harish Kumar | Completed |  | 2025-08-06 | 2025-08-06 | 2025-08-06 |  |  | Reviewed and closed.
SAA-262 | Auto-apply scheduler MVP | Harish Kumar | Completed |  | 2025-08-06 | 2025-08-07 | 2025-08-07 |  |  | Reviewed and closed.
SAA-262 | End-to-end testing + feedback | Harish Kumar | Completed |  | 2025-08-08 | 2025-08-08 | 2025-08-08 |  |  | Reviewed and closed.